## Sheet1
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | 2022-09-01 | [25 empty] | 2022-10-01 | [30 empty] | 2022-11-01
[5 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 4 | [6 empty] | Week 5 |  |  |  |  | Week 5 |  | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | Week 10 | [5 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14
[5 empty] | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
[5 empty] | Mon | Tues | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
1 | Requirements Specification
1.1 | Generating Requirements list | Kian Yang | 2022-09-05 | 2022-09-13 | bar: Week 1 5 Mon to Week 2 13 Tue
1.1.1 | Create use case diagram | Kian Yang | 2022-09-05 | 2022-09-13 | bar: Week 1 5 Mon to Week 2 13 Tue
1.1.2 | Attend client meeting | All | 2022-09-13 | 2022-09-13 | bar: Week 2 13 Tue
1.1.2.1 | Generate client meeting questions | Jwo Young | 2022-09-05 | 2022-09-13 | bar: Week 1 5 Mon to Week 2 13 Tue
1.2 | Generate Use Case Descriptions | Wai Qun, Cheng Kiat | 2022-09-13 | 2022-09-24 | bar: Week 2 13 Tue to Week 4 24 Sat
1.2.1 | Generate Use Case Descriptions 1-10 | Wai Qun | 2022-09-13 | 2022-09-24 | bar: Week 2 13 Tue to Week 4 24 Sat
1.2.2 | Generate Use Case Descriptions 11-21 | Cheng Kiat | 2022-09-13 | 2022-09-24 | bar: Week 2 13 Tue to Week 4 24 Sat
1.3 | Requirements documentation | All | 2022-09-13 | 2022-09-24 | bar: Week 2 13 Tue to Week 4 24 Sat
1.3.1 | Functional Requirements documentation | Cheng Kiat | 2022-09-13 | 2022-09-24 | bar: Week 2 13 Tue to Week 4 24 Sat
1.3.2 | Non-Functional Requirements documentation | Jwo Young | 2022-09-13 | 2022-09-24 | bar: Week 2 13 Tue to Week 4 24 Sat
1.3.3 | Performance Requirements documentation | Wai Qun | 2022-09-13 | 2022-09-24 | bar: Week 2 13 Tue to Week 4 24 Sat
1.3.4 | Safety and Security requirements documentation | Kian Yang | 2022-09-13 | 2022-09-24 | bar: Week 2 13 Tue to Week 4 24 Sat
1.3.5 | Other requirements documentation | Kian Yang | 2022-09-13 | 2022-09-24 | bar: Week 2 13 Tue to Week 4 24 Sat
1.4 | Review all peer documents | All | 2022-09-20 | 2022-09-24 | bar: Week 4 20 Tue to Week 4 24 Sat
2 | Project Planning
2.1 | Project Estimation | All | 2022-09-13 | 2022-09-18 | bar: Week 2 13 Tue to Week 2 18 Sun
2.1.1 | Size estimation | Wai Qun, Cheng Kiat | 2022-09-13 | 2022-09-18 | bar: Week 2 13 Tue to Week 2 18 Sun
2.1.1.1 | Estimate use case points (UCP) size | Wai Qun, Cheng Kiat | 2022-09-13 | 2022-09-18 | bar: Week 2 13 Tue to Week 2 18 Sun
2.1.1.1.1 | Estimate UCP 1-10 size | Cheng Kiat | 2022-09-13 | 2022-09-18 | bar: Week 2 13 Tue to Week 2 18 Sun
2.1.1.1.2 | Estimate UCP 11-21 size | Cheng Kiat | 2022-09-13 | 2022-09-18 | bar: Week 2 13 Tue to Week 2 18 Sun
2.1.2 | Effort estimation | Jwo Young | 2022-09-18 | 2022-09-18 | bar: Week 2 18 Sun
2.1.3 | Cost estimation | Kian Yang | 2022-09-18 | 2022-09-18 | bar: Week 2 18 Sun
2.2 | Project Management | Kian Yang | 2022-09-18 | 2022-09-24 | bar: Week 2 18 Sun to Week 4 24 Sat
2.2.1 | Generate Work Breakdown Structure | Kian Yang | 2022-09-18 | 2022-09-24 | bar: Week 2 18 Sun to Week 4 24 Sat
2.2.2 | Generate Project Management Gantt Chart | Kian Yang | 2022-09-18 | 2022-09-24 | bar: Week 2 18 Sun to Week 4 24 Sat
3 | Design
3.1 | Generate Architecture Component Diagram | Wai Qun | 2022-09-26 | 2022-10-02 | bar: Week 5 26 Mon to Week 5 1 Sat
3.1.1 | Review Architecture Design | Cheng Kiat | 2022-09-28 | 2022-10-01 | bar: Week 5 28 Wed to Week 5 1 Sat
3.1.1.1 | Finalize Architecture Design | Kian Yang | 2022-10-01 | 2022-10-02 | bar: Week 5 1 Sat to Week 5 2 Sun
3.2 | Web User Interface | Wai Qun | 2022-10-02 | 2022-10-16 | bar: Week 5 2 Sun to Week 7 16 Sun
3.2.1 | Functional Specifications | Cheng Kiat | 2022-10-02 | 2022-10-16 | bar: Week 5 2 Sun to Week 7 16 Sun
3.2.1.1 | Create user interface demo | Wai Qun | 2022-10-02 | 2022-10-16 | bar: Week 5 2 Sun to Week 7 16 Sun
3.2.1.2 | Review Functional Specifiactions | Jwo Young | 2022-10-10 | 2022-10-14 | bar: Week 7 10 Mon to Week 7 14 Fri
3.2.1.3 | Finalize Functional Specifications | Kian Yang | 2022-10-15 | 2022-10-16 | bar: Week 7 15 Sat to Week 7 16 Sun
3.2.2 | Technical Specifications | Cheng Kiat | 2022-10-02 | 2022-10-16 | bar: Week 5 2 Sun to Week 7 16 Sun
3.2.2.1 | Generate class diagram | Wai Qun | 2022-10-02 | 2022-10-09 | bar: Week 5 2 Sun to Week 6 9 Sun
3.2.2.2 | Generate Sequence diagram | Jwo Young | 2022-10-02 | 2022-10-09 | bar: Week 5 2 Sun to Week 6 9 Sun
3.2.2.3 | Generate Technical Specifications | Cheng Kiat | 2022-10-02 | 2022-10-09 | bar: Week 5 2 Sun to Week 6 9 Sun
3.2.2.4 | Review Technical Specifications | Jwo Young | 2022-10-10 | 2022-10-14 | bar: Week 7 10 Mon to Week 7 14 Fri
3.2.2.5 | Finalize Final Technical Specifications | Kian Yang | 2022-10-15 | 2022-10-16 | bar: Week 7 15 Sat to Week 7 16 Sun
3.3 | SQL Database | Wai Qun | 2022-10-02 | 2022-10-16 | bar: Week 5 2 Sun to Week 7 16 Sun
3.3.1 | Technical Specifications | Cheng Kiat | 2022-10-02 | 2022-10-16 | bar: Week 5 2 Sun to Week 7 16 Sun
3.3.1.1 | Generate Entity Relationship diagrams | Wai Qun | 2022-10-02 | 2022-10-09 | bar: Week 5 2 Sun to Week 6 9 Sun
3.3.1.2 | Generate Technical Specifications | Cheng Kiat | 2022-10-02 | 2022-10-09 | bar: Week 5 2 Sun to Week 6 9 Sun
3.3.1.3 | Review Technical Specifications | Jwo Young | 2022-10-10 | 2022-10-14 | bar: Week 7 10 Mon to Week 7 14 Fri
3.3.1.4 | Finalize Technical Specifications | Kian Yang | 2022-10-15 | 2022-10-16 | bar: Week 7 15 Sat to Week 7 16 Sun
4 | Developement
4.1 | Web Front End | Wai Qun | 2022-10-17 | 2022-11-12 | bar: Week 8 17 Mon to Week 11 12 Sat
4.1.1 | Develop Web pages | Wai Qun | 2022-10-17 | 2022-11-06 | bar: Week 8 17 Mon to Week 10 6 Sun
4.1.2 | Conduct unit testing | Wai Qun | 2022-11-04 | 2022-11-06 | bar: Week 10 4 Fri to Week 10 6 Sun
4.1.3 | Review web pages | Jwo Young | 2022-11-07 | 2022-11-11 | bar: Week 11 7 Mon to Week 11 11 Fri
4.1.3.1 | Test for accessibility | Jwo Young | 2022-11-07 | 2022-11-11 | bar: Week 11 7 Mon to Week 11 11 Fri
4.1.3.2 | Test for browser compatibility | Jwo Young | 2022-11-07 | 2022-11-11 | bar: Week 11 7 Mon to Week 11 11 Fri
4.1.3.3 | Test for responsiveness | Jwo Young | 2022-11-07 | 2022-11-11 | bar: Week 11 7 Mon to Week 11 11 Fri
4.1.4 | Obtain Client approval | Kian Yang | 2022-11-12 | 2022-11-15 | bar: Week 11 12 Sat to Week 12 15 Tue
4.2 | Web Back End | Cheng Kiat | 2022-10-17 | 2022-11-12 | bar: Week 8 17 Mon to Week 11 12 Sat
4.2.1 | Implement authentication and security mechanisms | Cheng Kiat | 2022-10-17 | 2022-10-19 | bar: Week 8 17 Mon to Week 8 19 Wed
4.2.2 | Implement high availability mechanisms | Cheng Kiat | 2022-10-19 | 2022-10-21 | bar: Week 8 19 Wed to Week 8 21 Fri
4.2.3 | Implement scalability mechanisms | Cheng Kiat | 2022-10-22 | 2022-10-25 | bar: Week 8 22 Sat to Week 9 25 Tue
4.2.4 | Conduct unit testing | Cheng Kiat | 2022-10-25 | 2022-10-30 | bar: Week 9 26 Wed to Week 9 30 Sun
4.2.5 | Test and Review Back End implementations | Jwo Young | 2022-10-31 | 2022-11-12 | bar: Week 10 31 Mon to Week 11 12 Sat
4.2.5.1 | Security testing | Jwo Young | 2022-10-31 | 2022-11-06 | bar: Week 10 31 Mon to Week 10 6 Sun
4.2.5.2 | Network load testing | Jwo Young | 2022-11-07 | 2022-11-09 | bar: Week 11 7 Mon to Week 11 9 Wed
4.2.5.3 | Uptime testing | Jwo Young | 2022-11-07 | 2022-11-09 | bar: Week 11 7 Mon to Week 11 9 Wed
4.2.5.4 | Scalability testing | Jwo Young | 2022-11-10 | 2022-11-12 | bar: Week 11 10 Thu to Week 11 12 Sat
4.2.6 | Obtain Client approval | Kian Yang | 2022-11-12 | 2022-11-15 | bar: Week 11 12 Sat to Week 12 15 Tue
4.3 | SQL Database | Wai Qun | 2022-10-17 | 2022-10-30 | bar: Week 8 17 Mon to Week 9 30 Sun
4.3.1 | Implement database tables | Wai Qun | 2022-10-17 | 2022-10-30 | bar: Week 8 17 Mon to Week 9 30 Sun
5 | Quality Assurance
5.1 | Web Application | Jwo Young | 2022-11-15 | 2022-11-20 | bar: Week 12 15 Tue to Week 12 20 Sun
5.1.1 | Verify design and functionality | Jwo Young | 2022-11-15 | 2022-11-16 | bar: Week 12 15 Tue to Week 12 16 Wed
5.1.2 | Verify back end implementations | Jwo Young | 2022-11-15 | 2022-11-16 | bar: Week 12 15 Tue to Week 12 16 Wed
5.1.3 | Conduct Integration Test | Wai Qun | 2022-11-16 | 2022-11-17 | bar: Week 12 16 Wed to Week 12 17 Thu
5.1.4 | Conduct User Acceptance Test | Cheng Kiat | 2022-11-17 | 2022-11-18 | bar: Week 12 17 Thu to Week 12 18 Fri
5.1.5 | Obtain Client's final approval | Kian Yang | 2022-11-18 | 2022-11-20 | bar: Week 12 18 Fri to Week 12 20 Sun
5.2 | SQL Database | Jwo Young | 2022-11-15 | 2022-11-20 | bar: Week 12 15 Tue to Week 12 20 Sun
5.2.1 | Verify design and data elements | Jwo Young | 2022-11-15 | 2022-11-16 | bar: Week 12 15 Tue to Week 12 16 Wed
5.2.2 | Verify relationships | Jwo Young | 2022-11-15 | 2022-11-16 | bar: Week 12 15 Tue to Week 12 16 Wed
5.2.3 | Conduct Integration Test | Wai Qun | 2022-11-16 | 2022-11-17 | bar: Week 12 16 Wed to Week 12 17 Thu
5.2.4 | Conduct User Acceptance Test | Cheng Kiat | 2022-11-17 | 2022-11-18 | bar: Week 12 17 Thu to Week 12 18 Fri
5.2.5 | Obtain Client's final approval | Kian Yang | 2022-11-18 | 2022-11-20 | bar: Week 12 18 Fri to Week 12 20 Sun